## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 7
PROJECT NAME | Personal Health Chatbot
PROJECT MENTOR (sponsor) | Manish Ranjan
TEAM MEMBERS | Venya Velmurugan (2024114002)
Advait Dintakurti
Vikesh Kansal
Keshav Goel
Amish Goyal

## Status
PROJECT NUMBER | 7
PROJECT NAME | Personal Health Chatbot
PROJECT MENTOR (sponsor) | Manish Ranjan
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 19 - January 25)
Fix meeting with client | Coordination | Venya, Advait, Vikesh, Amish, Keshav | - | 1 | Done |  | #VALUE! | #VALUE!
Client meeting | Coordination | Venya, Advait, Vikesh, Amish, Keshav | - | 2 | Done | Project Goal understood | #VALUE! | #VALUE!
Identify user requirements | Preparation | Vikesh, Amish, Keshav | 2 | 1 | Done |  | 1 | 100
Project synopsis writeup | Documentation | Venya, Advait | - | 3 | Done |  | #VALUE! | #VALUE!
Team Meeting | Coordination | Venya, Advait, Vikesh, Amish, Keshav | 1 | 0.4 | Done |  | 0.6 | 150
Prepare Minutes of Meeting | Documentation | Keshav | - | 0.2 | Done
Week 2 (January 26 - February 2)
Client meeting | Coordination | Venya, Advait, Vikesh, Amish, Keshav | 1 | 0.5 | Done | Client requested for rough outline of prototype | 0.5 | 100
Developing technical architecture | Design | Vikesh | - | 1.5 | Done | Temporary architecture, subject to change based on client feedback | #VALUE! | #VALUE!
Researched Alternatives to Vanilla RAG | Preparation | Vikesh, Advait | - | 6 | Done | Found research papers in line with the client's request of sending the EMR to the LLM efficiently. | #VALUE! | #VALUE!
Develop broad timeline based on proposed architecture | Preparation | Venya | 2 | 1 | Done | Open to change based on project progress | 1 | 100
Final prototype+timeline document submitted to client | Documentation | Amish, Keshav | - | 2 | Done
Team Meeting | Coordination | Venya, Advait, Vikesh, Amish, Keshav | 1 | 0.5 | Done |  | 0.5 | 100
Prepare Minutes of Meeting | Documentation | Keshav | - | 0.2 | Done
Week 3 (February 3 - February 9)
Client meeting | Coordination | Venya, Advait, Vikesh, Amish, Keshav | 1 | 0.4 | Done | Prototype discussion, Client suggested not to use RAG and requested us to look up alternate implementation strategies
Status tracker | Documentation | Venya | 1 | 0.8 | Done |  | 0.2 | 25
Look into RAG vs direct context | Preparation | Amish, Venya | 2 |  | Delayed
Test EHR-RAG prompts | Preparation | Advait | 0.75 |  | Delayed
Research Knowledge Graphs (UMLS) | Preparation | Vikesh | 1.5 |  | Delayed | Waiting on database from client (they need to get us a license which they have applied for).
Look into UMLS licensing | Preparation | Venya, Amish | 1 | 0.3 | Done
Make basic prototype | Development | Amish |  |  | Done |  | #REF! | #REF!
Prepare Minutes of Meeting | Documentation | Keshav | - | 0.2 | Done
Week 4 (February 10 - February 17)
Client meeting | Coordination | Venya, Advait, Vikesh, Amish, Keshav | 0.3 | 0.3 | Done | Client is still waiting on UMLS license/database access. Also, client asked us to include multilingual support.
Researched & experimented with multiple small local models (for replacing current LLM APIs) | Development | Vikesh, Advait | 1.5 | 1 | Done | Found MedGemma as possibly effective and locally runnable (4B parameters).
Build a prototype w/ multiple chats + UI | Development | Advait | 3 | 4 | Done |  | -1 | 25
Make project plan document | Documentation | Keshav, Venya | 2.5 | 3 | Done
Multilingual Support | Development | Venya | 1 | 2 | Done |  | -1 | 50
Maintain chat context from previous prompts | Development | Keshav | 0.5 | 0.5 | Done
Prepare Minutes of Meeting | Documentation | Amish | - | 0.2 | Done
Week 5 (February 18 - February 25)
Client meeting | Coordination | Venya, Vikesh, Advait, Amish, Keshav | 0.3 |  | Delayed
Fine-tuned the system's prompt | Development | Keshav | 0.5 | 0.5 | Done
Make SRS Document + Use-case diagram | Documentation | Venya, Vikesh | 4 | 1.5 | Done
Make a video of current prototype for client | Testing | Amish | 0.5 |  | Done
Prepare Minutes of Meeting | Documentation | Amish | - | 0.2 | Done
Week 6 (February 26 - March 3) Midsems
Week 7 (March 4 - March 10)
Client meeting | Coordination | Venya, Advait, Vikesh, Amish, Keshav | 0.3 | 0.3 | Done
Prepare Minutes of Meeting | Documentation | Venya | - | 0.2 | Done
Applied for the umls licence and obtained the datasets | Development | Keshav |  |  | Done
Looked into gdpr principles and made the chatbot compliant to its policies | Development | Venya |  |  | Done
Chat compaction | Development | Venya |  |  | Done
Researched and built the initial rag pipeline | Development | Vikesh, Amish |  |  | Done
Researched and built the improved rag pipeline | Development | Keshav |  |  | Done
Improved upon the first phase of the pipeline | Development | Vikesh, Advait |  |  | Done
Integrated gdpr, tts, chat compaction from previous iteration with the final iteration | Development | Amish, Keshav | 0.5 | 1 | Done
Made the presentation |  | Venya, Keshav, Amish |  |  | Done
Made the demo video |  | Vikesh, Advait |  |  | Done
Week 8 (March 11 - March 17)
Client meeting | Coordination | Venya, Advait, Vikesh, Amish, Keshav | 0.3 | 0.3 | Done | Client is yet to look into and test the entire pipeline from his end.
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on H5: SE: This field is updated automatically